## 00_Overview
Field | Value
Workbook | DealFlow AI Project Plan
Generated At | 2026-05-02 16:50:50
Purpose | Implementation-ready Excel workbook for a small engineering team building DealFlow AI MVP.
Stack | Next.js + FastAPI + PostgreSQL + Redis + Auth0 + HubSpot + Twilio + Google/Microsoft Calendar
Priority Meaning | P0 = required for paid pilot; P1 = important after MVP; P2 = future enhancement
Total Tasks | 91
Total Estimated Effort | 226.5
P0 Tasks | 85
P1 Tasks | 6
P2 Tasks | 0

## 01_Task_Breakdown
Task ID | Epic | Module | Task Name | Description | Owner Role | Priority | Dependency | Estimated Effort | Acceptance Criteria | Notes | Status | Assignee | Sprint | Start Date | Due Date | Comments
DAI-001 | Product and Requirements Setup | Product Docs | Finalize MVP Functional Spec | Freeze MVP scope, non-goals, user roles, key workflows, and pilot success criteria. | Product Manager / Analyst | P0 | None | 1 | Spec approved and stored in /docs/product-functional-spec.md. | Prevents scope drift.
DAI-002 | Product and Requirements Setup | Backlog | Create MVP Backlog | Convert requirements into epics, tasks, priorities, dependencies, and acceptance criteria. | TPM / Eng Lead | P0 | DAI-001 | 1 | Backlog reviewed with engineering team. | Use this sheet as baseline.
DAI-003 | Product and Requirements Setup | Pilot Ops | Define Pilot Operating Model | Define onboarding checklist, daily monitoring, manual approval process, and weekly reporting. | Implementation Analyst | P0 | DAI-001 | 1 | Pilot SOP exists and is usable by implementation team. | Required for first customer.
DAI-004 | Product and Requirements Setup | Test Data | Define Demo Data Set | Define fake tenants, agents, leads, messages, approvals, appointments, and CRM sync failures. | Product + QA | P0 | DAI-001 | 1 | Seed data requirements documented. | Speeds UI/demo development.
DAI-005 | System Architecture | Architecture | Confirm Technical Stack | Confirm Next.js, FastAPI, PostgreSQL, Redis, Auth0, HubSpot, Twilio, Google/Microsoft Calendar. | Engineering Lead | P0 | DAI-001 | 0.5 | Stack decisions documented in /docs/decisions.md. | Avoid switching stacks mid-build.
DAI-006 | System Architecture | Repo | Initialize Monorepo | Create base repo structure for web, API, worker, shared types, infra, docs, and tests. | Principal Engineer | P0 | DAI-005 | 1 | Repo boots locally with README instructions. | First Claude Code task.
DAI-007 | System Architecture | Local Dev | Docker Compose Setup | Add local PostgreSQL, Redis, API, worker, and web containers or scripts. | DevOps Engineer | P0 | DAI-006 | 1 | docker compose up starts DB/Redis and app services. | Keep local setup simple.
DAI-008 | System Architecture | API Foundation | FastAPI Health + Versioning | Create /health, /version, API router structure, config loader, and error format. | Backend Engineer | P0 | DAI-006 | 1 | Health endpoint passes locally and in CI. | Baseline API skeleton.
DAI-009 | System Architecture | Frontend Foundation | Next.js App Shell | Create app shell, layout, protected dashboard route placeholder, Tailwind, shadcn/ui setup. | Frontend Engineer | P0 | DAI-006 | 1 | Web app loads shell and placeholder dashboard. | Do not overdesign UI yet.
DAI-010 | Tenant and User Management | Auth | Auth0 JWT Validation | Validate Auth0 JWTs in backend and map Auth0 subject to internal user. | Backend Engineer | P0 | DAI-008 | 2 | Protected API rejects invalid tokens and accepts valid Auth0 JWT. | Auth0 for identity only.
DAI-011 | Tenant and User Management | Database | Tenant/User/Roles Schema | Create tables for tenants, users, roles, user_roles, memberships, and agent profiles. | Backend Engineer | P0 | DAI-010 | 2 | Migration creates tables with tenant indexes. | All tenant-owned data needs tenant_id.
DAI-012 | Tenant and User Management | RBAC | RBAC Middleware | Implement permission checks for owner/admin, manager, agent, implementation admin, auditor. | Backend Engineer | P0 | DAI-011 | 2 | Unauthorized role receives 403; inactive users blocked. | Backend must not trust frontend.
DAI-013 | Tenant and User Management | Frontend | Login + Session Handling | Add Auth0 login/logout and frontend session state. | Frontend Engineer | P0 | DAI-010 | 2 | User can log in and access protected app shell. | Use Auth0 SDK.
DAI-014 | Tenant and User Management | Admin UI | User Management Screen | Admin can view, invite, activate/deactivate users, and assign roles. | Frontend + Backend | P0 | DAI-011, DAI-012 | 3 | Admin manages users; audit log captures changes. | Needed for pilot setup.
DAI-015 | HubSpot CRM Integration | OAuth/Connection | HubSpot Connection | Implement HubSpot OAuth/private app connection storage with encrypted credentials. | Integration Engineer | P0 | DAI-011 | 3 | Admin can connect HubSpot and connection status is stored. | Token storage must be encrypted.
DAI-016 | HubSpot CRM Integration | Mapping | HubSpot Field Mapping Model | Create tenant-specific mapping for DealFlow fields to HubSpot properties. | Backend Engineer | P0 | DAI-015 | 2 | Mapping can be saved and retrieved via API. | UI can come later if needed.
DAI-017 | HubSpot CRM Integration | CRM Adapter | HubSpot Contact Lookup/Upsert | Implement lookup and create/update contact by email/phone. | Integration Engineer | P0 | DAI-015 | 3 | Contact upsert works in HubSpot sandbox/test account. | Must be idempotent.
DAI-018 | HubSpot CRM Integration | CRM Adapter | HubSpot Deal/Lead Object Upsert | Create or update HubSpot deal/lead object linked to contact. | Integration Engineer | P0 | DAI-017 | 3 | Lead/deal record syncs with correct mapped fields. | Exact HubSpot object model configurable.
DAI-019 | HubSpot CRM Integration | Sync Logs | HubSpot Sync Logging | Store sync request, response reference, status, error, retry count, and next retry time. | Backend Engineer | P0 | DAI-017 | 2 | Every HubSpot operation creates a sync log. | Do not log secrets.
DAI-020 | Lead Ingestion and Sync | Lead Sources | Lead Source Configuration | Create source records with type, name, source key, secret, and status. | Backend Engineer | P0 | DAI-011 | 2 | Admin can create source; webhook has source key. | Start API-first; UI later.
DAI-021 | Lead Ingestion and Sync | Webhook | Website Lead Webhook | Add signed lead webhook endpoint with idempotency key support. | Backend Engineer | P0 | DAI-020 | 2 | Valid payload creates ingestion event; invalid secret rejected. | First vertical slice.
DAI-022 | Lead Ingestion and Sync | Normalization | Lead Normalization Service | Normalize raw source payload into contact, lead, preferences, source metadata. | Backend Engineer | P0 | DAI-021 | 2 | Normalized lead appears in DB with standard fields. | Keep mappers source-specific.
DAI-023 | Lead Ingestion and Sync | Deduplication | Exact Duplicate Detection | Detect duplicates by normalized phone/email hash within tenant. | Backend Engineer | P0 | DAI-022 | 2 | Duplicate lead links to existing contact/lead timeline. | P0 exact match only.
DAI-024 | Lead Ingestion and Sync | CSV Import | CSV Lead Import | Upload CSV, map columns, validate rows, import leads, report row errors. | Backend + Frontend | P0 | DAI-022 | 4 | CSV import creates valid leads and reports rejected rows. | Useful for pilot backfill.
DAI-025 | Lead Ingestion and Sync | Email Parser | Inbound Email Parser | Parse lead inquiry emails into source, contact, message, and lead data. | Backend Engineer | P0 | DAI-022 | 3 | Sample inquiry emails create leads/messages. | Can start with provider inbound parse webhook.
DAI-026 | Lead Ingestion and Sync | HubSpot Import | HubSpot Lead Pull/Sync | Pull or receive leads from HubSpot and normalize into DealFlow. | Integration Engineer | P0 | DAI-017, DAI-022 | 4 | HubSpot-created leads appear in DealFlow. | Limit scope to one-way import first.
DAI-027 | Twilio Messaging Integration | Messaging Core | Messaging Abstraction | Create common interface for email, SMS, WhatsApp, iMessage, RCS. | Backend Engineer | P0 | DAI-011 | 2 | System can route outbound message by channel/provider. | Implement only Twilio/email first.
DAI-028 | Twilio Messaging Integration | SMS | Twilio SMS Outbound | Send SMS through Twilio with message status tracking. | Integration Engineer | P0 | DAI-027 | 2 | SMS sends and message record updates status. | Use test credentials first.
DAI-029 | Twilio Messaging Integration | WhatsApp | Twilio WhatsApp Outbound | Send WhatsApp template/freeform messages as allowed by policy. | Integration Engineer | P0 | DAI-027 | 3 | WhatsApp outbound works in sandbox/approved account. | WhatsApp policy matters.
DAI-030 | Twilio Messaging Integration | Inbound Webhooks | Twilio Inbound Callback | Receive inbound SMS/WhatsApp messages and attach to conversation/lead. | Integration Engineer | P0 | DAI-028, DAI-029 | 3 | Incoming message appears in lead timeline. | Signature validation required.
DAI-031 | Twilio Messaging Integration | Status Webhooks | Twilio Delivery Status Callback | Handle sent, delivered, failed, undelivered statuses. | Integration Engineer | P0 | DAI-028, DAI-029 | 2 | Message status updates from Twilio callback. | Required for audit/debugging.
DAI-032 | Consent and Messaging Policy Engine | Consent Data | Consent/Opt-Out Schema | Create tables for consent records, opt-out records, and channel permissions. | Backend Engineer | P0 | DAI-011 | 2 | Consent state is stored per contact/channel. | PII-safe logs.
DAI-033 | Consent and Messaging Policy Engine | Policy | Channel Policy Engine | Determine whether channel can auto-send, needs approval, or is blocked. | Backend Engineer | P0 | DAI-032 | 2 | Policy decision returned before every outbound send. | Tenant configurable.
DAI-034 | Consent and Messaging Policy Engine | Opt-Out | STOP/Unsubscribe Handling | Detect opt-out messages and block future automated sends. | Backend Engineer | P0 | DAI-030, DAI-032 | 2 | STOP records opt-out and prevents future outbound. | Must work before pilot.
DAI-035 | Consent and Messaging Policy Engine | Settings UI | Messaging Policy Settings | Admin can enable/disable email, SMS, WhatsApp, iMessage, RCS and auto-send rules. | Frontend + Backend | P1 | DAI-033 | 3 | Settings update policy engine behavior. | P0 can be config-file/admin API.
DAI-036 | SLA Tracking Engine | Settings | Tenant SLA Settings | Add configurable SLA thresholds: first response, agent follow-up, stale timing, escalation. | Backend + Frontend | P0 | DAI-011 | 3 | Tenant can save SLA settings and worker uses them. | Client-specific by requirement.
DAI-037 | SLA Tracking Engine | Computation | SLA Result Computation | Calculate first response SLA, agent follow-up SLA, stale state, and escalation state. | Backend Engineer | P0 | DAI-036, DAI-038 | 3 | SLA records update after messages/tasks/actions. | Used by dashboard and CRM writeback.
DAI-038 | SLA Tracking Engine | Scheduler | Stale Lead Detection Worker | Scheduled worker marks leads stale if no customer reply or no agent action. | Backend Engineer | P0 | DAI-036 | 3 | Stale lead state appears on lead and dashboard. | Deterministic, not AI-based.
DAI-039 | SLA Tracking Engine | Alerts | SLA Breach Event Creation | Create internal event when SLA breach or stale lead occurs. | Backend Engineer | P0 | DAI-037 | 2 | Breach event creates timeline and notification trigger. | Drives escalation.
DAI-040 | AI Lead Qualification | AI Core | LLM Provider Abstraction | Create AI provider interface for classification, extraction, summary, next action. | AI Engineer | P0 | DAI-008 | 2 | AI calls route through provider abstraction. | Do not hardwire provider deeply.
DAI-041 | AI Lead Qualification | Prompting | Prompt Version Registry | Store prompt names, versions, schemas, and active version config. | AI Engineer | P0 | DAI-040 | 2 | AI action logs include prompt version. | Can start as code config plus DB log.
DAI-042 | AI Lead Qualification | Classification | Lead Classification Job | Classify lead as buyer/seller/tenant/landlord/investor/vendor/spam/unknown. | AI Engineer | P0 | DAI-040, DAI-022 | 3 | Structured output validates and updates lead. | Low confidence triggers review.
DAI-043 | AI Lead Qualification | Extraction | Qualification Extraction Job | Extract budget, location, type, timeline, financing, purpose, language, appointment preference. | AI Engineer | P0 | DAI-040, DAI-030 | 4 | Extracted fields populate lead preferences with confidence. | Use JSON schema validation.
DAI-044 | AI Lead Qualification | Guardrails | AI Safety Gate | Block or route to approval for pricing, legal, finance, negotiation, unsupported facts, low confidence. | AI + Backend Engineer | P0 | DAI-040 | 3 | Unsafe test cases create approval/handoff, not auto-send. | Critical.
DAI-045 | AI Conversation Summary | Summary | Conversation Summary Generator | Generate short agent-facing summary from conversation and lead context. | AI Engineer | P0 | DAI-040, DAI-030 | 3 | Summary stored and visible on lead detail page. | Avoid full transcript in every prompt.
DAI-046 | AI Conversation Summary | CRM Notes | CRM-Friendly Summary Format | Create structured summary suitable for HubSpot notes. | AI Engineer | P0 | DAI-045 | 1 | Summary includes requirements, objections, missing fields, next action. | Used in CRM writeback.
DAI-047 | AI Recommended Next Action | Logic | Next Action Rule Engine | Determine next action: ask question, assign agent, book appointment, escalate, follow up, stop automation. | Backend + AI | P0 | DAI-043, DAI-044 | 3 | Next action is stored with reason and confidence. | Deterministic rules first, AI wording second.
DAI-048 | AI Recommended Next Action | Drafting | Follow-Up Draft Generation | Generate approved-script-based drafts for next action. | AI Engineer | P0 | DAI-047, DAI-044 | 3 | Draft either sends safely or enters approval queue. | Avoid unsupported claims.
DAI-049 | CRM Write-Back | Mapping | HubSpot Required Field Mapping | Map status, timestamps, SLA results, qualification, next action, tasks, notes, stale/escalation, consent. | Integration Engineer | P0 | DAI-016 | 3 | Required pilot fields mapped and documented. | This is operational completeness.
DAI-050 | CRM Write-Back | Sync Worker | CRM Writeback Worker | Trigger HubSpot writes on lead status, qualification, appointment, SLA, task, consent events. | Integration Engineer | P0 | DAI-049 | 4 | HubSpot updates after major DealFlow events. | Use queue + retries.
DAI-051 | CRM Write-Back | Retry | Manual CRM Retry | Allow admin to retry failed syncs from sync log. | Backend + Frontend | P0 | DAI-019, DAI-050 | 2 | Failed sync can be retried and status updates. | Essential for pilot ops.
DAI-052 | Agent Task Creation | Internal Tasks | Task Data Model | Create tasks for agent follow-up, approval, stale lead, appointment prep, CRM issue. | Backend Engineer | P0 | DAI-011 | 2 | Tasks can be created, assigned, completed, overdue. | Internal source of truth.
DAI-053 | Agent Task Creation | HubSpot Tasks | Create HubSpot CRM Tasks | Create HubSpot tasks from DealFlow next actions and stale/SLA events. | Integration Engineer | P0 | DAI-050, DAI-052 | 3 | HubSpot task appears with due date and lead context. | Required for CRM adoption.
DAI-054 | Agent Task Creation | Agent UI | Agent Task View | Agents see assigned tasks, due dates, lead context, and completion state. | Frontend Engineer | P0 | DAI-052 | 3 | Agent can complete task and timeline updates. | Keep simple list view.
DAI-055 | Admin Configuration | Settings | Tenant Settings Screen | Configure company profile, timezone, SLA, messaging channels, and basic preferences. | Frontend + Backend | P0 | DAI-036, DAI-033 | 3 | Admin settings persist and affect workflows. | MVP settings only.
DAI-056 | Admin Configuration | Routing | Agent Routing Rules | Configure routing by location, property type, language, capacity, availability, fallback queue. | Backend + Frontend | P0 | DAI-011 | 4 | Qualified lead is assigned based on configured rule. | Deterministic.
DAI-057 | Admin Configuration | KB Upload | Knowledge Base Upload | Upload PDF, DOCX, TXT, CSV docs for approved scripts, FAQs, property/project info. | Backend + AI | P1 | DAI-040 | 5 | Docs upload, parse, chunk, and index. | P1 unless pilot needs factual AI answers.
DAI-058 | Audit Logs and Activity Timeline | Audit | Audit Log Service | Central service to log AI, human, integration, and system actions. | Backend Engineer | P0 | DAI-011 | 3 | Mutations write audit records with actor/entity/before/after. | Non-negotiable.
DAI-059 | Audit Logs and Activity Timeline | Timeline | Lead Activity Timeline | Create timeline items for messages, AI actions, assignments, tasks, appointments, syncs, approvals. | Backend + Frontend | P0 | DAI-058 | 4 | Lead detail shows chronological timeline. | Core operator view.
DAI-060 | Audit Logs and Activity Timeline | AI Actions | AI Action Logging | Store model, prompt version, input reference, output JSON, confidence, safety decision. | AI + Backend | P0 | DAI-040, DAI-058 | 2 | Every AI job creates AI action record. | Required for trust.
DAI-061 | Audit Logs and Activity Timeline | Audit UI | Audit Log Search | Admin/auditor can search by lead, user, action, entity, date. | Frontend + Backend | P1 | DAI-058 | 3 | Search returns filtered audit records. | P0 if customer requires compliance review.
DAI-062 | Notifications and Escalations | Notification Core | Notification Service | Create in-app/email notifications for assignment, approval, stale, SLA breach, booking, sync failure. | Backend Engineer | P0 | DAI-052, DAI-039 | 3 | Notification records are created and delivered through configured channel. | Start with in-app/email.
DAI-063 | Notifications and Escalations | Escalation | Human Handoff/Escalation | Escalate angry, high-value, legal/financial, low-confidence, or unsupported information cases. | Backend + AI | P0 | DAI-044, DAI-062 | 3 | Escalated lead stops automation and notifies manager/agent. | Safety-critical.
DAI-064 | Notifications and Escalations | Approval Queue | Human Approval Queue | Managers/admins can approve, edit, reject, or take over AI drafts. | Frontend + Backend | P0 | DAI-044, DAI-058 | 4 | Approval decision sends/blocks message and logs action. | Required before broad auto-send.
DAI-065 | Dashboard and Reporting | Dashboard API | Owner Dashboard Summary API | Aggregate leads, response status, qualification, appointments, stale leads, SLA, source performance. | Backend Engineer | P0 | DAI-037, DAI-059 | 4 | API returns metrics by date/source/agent filters. | Build from DealFlow DB.
DAI-066 | Dashboard and Reporting | Dashboard UI | Owner Dashboard UI | Display core metrics and exception lists: stale leads, SLA breaches, hot leads, sync failures. | Frontend Engineer | P0 | DAI-065 | 4 | Owner can view operational health in dashboard. | Avoid over-designed analytics.
DAI-067 | Dashboard and Reporting | Source ROI | Source Performance View | Show source-level leads, qualification rate, appointments, stale rate, response time. | Frontend + Backend | P1 | DAI-065 | 3 | Source table filterable by date and source. | Important after workflow works.
DAI-068 | Security and Access Control | Tenant Isolation | Tenant Isolation Enforcement | Ensure every tenant-scoped query filters by tenant and users cannot cross-access records. | Backend + QA | P0 | DAI-011, DAI-012 | 3 | Automated tests prove Tenant A cannot access Tenant B. | Blocking issue if failed.
DAI-069 | Security and Access Control | Secrets | Secret Encryption | Encrypt HubSpot/Twilio/calendar credentials and avoid logging tokens. | Backend + DevOps | P0 | DAI-015, DAI-027 | 2 | Secrets encrypted at rest and redacted in logs. | MVP uses DB encryption + encrypted secrets.
DAI-070 | Security and Access Control | Webhooks | Webhook Signature Validation | Validate HubSpot/Twilio/source signatures and secrets. | Backend Engineer | P0 | DAI-021, DAI-030 | 2 | Invalid signatures rejected and logged. | Public endpoint protection.
DAI-071 | Security and Access Control | Rate Limits | API/Webhook Rate Limiting | Add rate limits to auth-adjacent and public webhook endpoints. | Backend + DevOps | P0 | DAI-008 | 2 | Excess requests are throttled with safe error. | Prevent abuse.
DAI-072 | Observability and Monitoring | Logging | Structured Logging | Add JSON logs with tenant_id, lead_id, user_id, workflow_id, correlation_id. | Backend + DevOps | P0 | DAI-008 | 2 | Logs are structured and searchable. | Redact PII where possible.
DAI-073 | Observability and Monitoring | Errors | Error Monitoring | Integrate error tracking for backend, worker, and frontend. | DevOps Engineer | P0 | DAI-006 | 2 | Exceptions appear in monitoring tool with context. | Sentry or similar.
DAI-074 | Observability and Monitoring | Metrics | Workflow Metrics | Track ingestion count, AI latency, message failures, CRM sync failures, SLA breaches, queue depth. | Backend + DevOps | P0 | DAI-072 | 3 | Metrics dashboard exists for internal team. | Pilot operations need this.
DAI-075 | Observability and Monitoring | Integration Health | Integration Health View | Show HubSpot/Twilio/calendar connection status and latest failures. | Frontend + Backend | P1 | DAI-019, DAI-031 | 3 | Admin can see broken integrations. | Useful for support.
DAI-076 | Testing and QA | Unit Tests | Core Unit Tests | Test normalization, dedupe, RBAC, consent, SLA, routing, guardrails. | QA + Backend | P0 | Related modules | 4 | Unit test suite passes in CI. | Add tests per feature.
DAI-077 | Testing and QA | API Tests | API Integration Tests | Test lead ingestion, user permissions, approval, messaging callbacks, CRM sync mocks. | QA Engineer | P0 | DAI-021, DAI-064 | 5 | API tests run against test DB. | Critical for regression.
DAI-078 | Testing and QA | LLM Evals | AI Safety Evaluation Set | Build fixtures for normal leads, legal/finance/pricing, angry leads, prompt injection, high-value leads. | AI + QA | P0 | DAI-044 | 3 | Unsafe cases require approval/handoff in evals. | Required before auto-send.
DAI-079 | Testing and QA | E2E Tests | Critical E2E Smoke Tests | Test lead webhook -> inbox -> AI classification -> approval -> message -> CRM sync. | QA + Full-stack | P0 | DAI-064, DAI-050 | 4 | E2E smoke passes before release. | Keep small.
DAI-080 | Pilot Readiness | Seed Data | Demo/Pilot Seed Script | Create realistic seeded tenants, agents, leads, approvals, stale leads, appointments, sync failures. | Backend + Product | P0 | DAI-011 | 2 | Seed command produces useful demo workspace. | Helps sales and testing.
DAI-081 | Pilot Readiness | Onboarding | Customer Onboarding Checklist | Checklist for HubSpot, Twilio, lead sources, SLA, agents, routing, scripts, consent. | Implementation Analyst | P0 | DAI-003 | 1 | Checklist used for pilot onboarding. | Should be operational, not theoretical.
DAI-082 | Pilot Readiness | Manual Supervision | Daily Monitoring Process | Define daily review of approvals, failed syncs, SLA breaches, stale leads, unsafe AI cases. | Implementation Lead | P0 | DAI-074 | 1 | Daily ops checklist exists. | Managed pilot model.
DAI-083 | Pilot Readiness | Launch Gate | Pilot Readiness Review | Final go/no-go checklist across product, security, AI, integrations, support. | TPM + Eng Lead | P0 | Most P0 tasks | 1 | All launch blockers resolved or accepted. | Do before real customer traffic.
DAI-084 | Deployment and DevOps | CI | CI Pipeline | Run lint, type check, tests, migrations check, build web/API. | DevOps Engineer | P0 | DAI-006 | 2 | PRs run CI and block failures. | Keep CI fast.
DAI-085 | Deployment and DevOps | Environments | Staging Environment | Deploy API, web, worker, Postgres, Redis, env secrets to staging. | DevOps Engineer | P0 | DAI-084 | 3 | Staging available with seeded demo data. | Required before pilot.
DAI-086 | Deployment and DevOps | Production | Production Deployment | Deploy production with managed DB, backups, logging, monitoring, secrets. | DevOps Engineer | P0 | DAI-085 | 3 | Production smoke test passes. | Start simple; no Kubernetes needed.
DAI-087 | Deployment and DevOps | Backups | Database Backup Policy | Configure automated database backups and restore test. | DevOps Engineer | P0 | DAI-086 | 2 | Backup exists and restore procedure is documented. | Pilot data protection.
DAI-088 | Documentation and Handoff | README | Developer README | Document setup, env vars, run commands, tests, migrations, architecture links. | Engineering Lead | P0 | DAI-006 | 1 | New dev can run app locally. | Claude Code should maintain.
DAI-089 | Documentation and Handoff | API Docs | API Contract Docs | Document main APIs with request/response examples. | Backend Engineer | P0 | DAI-021 | 2 | OpenAPI or markdown docs available. | Useful for integrations.
DAI-090 | Documentation and Handoff | Runbooks | Operational Runbooks | Document failed CRM sync, Twilio failure, AI approval issue, stuck worker, SLA breach investigation. | DevOps + Implementation | P0 | DAI-074 | 2 | Runbooks usable by support/implementation team. | Required for pilot support.
DAI-091 | Documentation and Handoff | Customer Docs | Pilot Admin Guide | Document how customer admins use inbox, approvals, tasks, dashboard, settings. | Product + Implementation | P1 | Dashboard/UI stable | 2 | Admin guide shared with pilot customer. | Not needed before internal demo.

## 02_Phase_Plan
Phase | Goal Area | Goal | Tasks | Exit Criteria
Phase 1 | Foundation | Build production-shaped skeleton: repo, auth, tenant isolation, database foundation, API, web shell, workers, audit logging base. | DAI-001 to DAI-014; DAI-058 base audit service; DAI-084 CI pipeline; DAI-088 developer README | Repo runs locally; Auth0 login works; backend validates JWT; tenants/users/RBAC exist; health check and web shell work; migrations run; tenant isolation test exists.
Phase 2 | HubSpot CRM Integration | Connect HubSpot as first CRM and establish reliable sync foundations. | DAI-015 to DAI-019; DAI-049 basic mapping; DAI-070 HubSpot webhook validation; DAI-075 if time permits | Admin can connect HubSpot; credentials encrypted; contacts/deals upsert; sync logs capture success/failure; field mapping configurable.
Phase 3 | Twilio Messaging and Consent | Enable controlled SMS/WhatsApp communication with consent and opt-out enforcement. | DAI-027 to DAI-034; DAI-035 if settings UI needed; DAI-071 rate limiting | SMS and WhatsApp outbound work; inbound replies attach to lead; delivery statuses update; opt-outs block automated outbound; policy engine runs before every send.
Phase 4 | SLA and AI Workflows | Implement lead classification, qualification extraction, SLA tracking, stale detection, summaries, and next actions. | DAI-036 to DAI-048; DAI-060 AI action logging; DAI-063 escalation rules; DAI-078 LLM evals | SLA configurable; stale detection works; AI classifies/extracts/summarizes; next action stored; unsafe cases enter approval/handoff; AI actions logged.
Phase 5 | CRM Write-Back | Write operationally complete lead updates back to HubSpot. | DAI-049 to DAI-053; DAI-050 CRM worker; DAI-051 manual retry; DAI-046 CRM-friendly summary | HubSpot receives status, timestamps, SLA, qualification, next action, tasks, notes, stale/escalation state, consent; failed sync retries; manual retry works.
Phase 6 | Dashboard and Reporting | Give owners/managers visibility into lead leakage, SLA breaches, stale leads, source performance, and agent follow-up. | DAI-054, DAI-055, DAI-056, DAI-059, DAI-064, DAI-065 to DAI-067 | Lead inbox/detail/timeline exist; approval queue works; agent task view works; owner dashboard shows core metrics; source performance visible if in pilot scope.
Phase 7 | Paid Pilot Hardening | Make system stable, observable, supportable, and safe enough for first paid pilot. | DAI-068 to DAI-079; DAI-080 to DAI-083; DAI-085 to DAI-087; DAI-089 to DAI-091 | Staging and production deployed; backups configured; monitoring active; E2E and AI evals pass; onboarding/runbooks complete; no P0 security/AI blockers.

## 03_Epic_Summary
Epic | Total Tasks | P0 | P1 | P2 | Estimated Effort
Product and Requirements Setup | 4 | 4 | 0 | 0 | 4
System Architecture | 5 | 5 | 0 | 0 | 4.5
Tenant and User Management | 5 | 5 | 0 | 0 | 11
HubSpot CRM Integration | 5 | 5 | 0 | 0 | 13
Lead Ingestion and Sync | 7 | 7 | 0 | 0 | 19
Twilio Messaging Integration | 5 | 5 | 0 | 0 | 12
Consent and Messaging Policy Engine | 4 | 3 | 1 | 0 | 9
SLA Tracking Engine | 4 | 4 | 0 | 0 | 11
AI Lead Qualification | 5 | 5 | 0 | 0 | 14
AI Conversation Summary | 2 | 2 | 0 | 0 | 4
AI Recommended Next Action | 2 | 2 | 0 | 0 | 6
CRM Write-Back | 3 | 3 | 0 | 0 | 9
Agent Task Creation | 3 | 3 | 0 | 0 | 8
Admin Configuration | 3 | 2 | 1 | 0 | 12
Audit Logs and Activity Timeline | 4 | 3 | 1 | 0 | 12
Notifications and Escalations | 3 | 3 | 0 | 0 | 10
Dashboard and Reporting | 3 | 2 | 1 | 0 | 11
Security and Access Control | 4 | 4 | 0 | 0 | 9
Observability and Monitoring | 4 | 3 | 1 | 0 | 10
Testing and QA | 4 | 4 | 0 | 0 | 16
Pilot Readiness | 4 | 4 | 0 | 0 | 5
Deployment and DevOps | 4 | 4 | 0 | 0 | 10
Documentation and Handoff | 4 | 3 | 1 | 0 | 7

## 04_Project_Skeleton
Folder/File | Purpose | Example Files | What Belongs Inside
CLAUDE.md | Claude Code project instructions | CLAUDE.md | Product rules, stack, coding standards, AI guardrails, Definition of Done.
docs/ | Product and engineering reference | product-functional-spec.md; engineering-design.md; decisions.md; mvp-backlog.md | Specs Claude Code should read before changes.
apps/web/ | Frontend app | Next.js files | Dashboard, inbox, settings, approval queue, lead detail UI.
apps/api/ | Backend API | FastAPI app | REST APIs, services, auth, RBAC, integrations, DB access.
apps/worker/ | Async workers | Celery/RQ worker | AI jobs, CRM sync, Twilio callbacks, SLA/stale jobs.
packages/shared/ | Shared constants/types | enums; API types | Shared channel enums, statuses, DTOs, validation constants.
infra/ | Local/deployment infra | Docker; migrations; seeds | Postgres/Redis setup, Alembic migrations, deployment manifests.
scripts/ | Operational scripts | seed; migrate; reset | Local setup, DB reset, data import, support utilities.
tests/ | Cross-app tests | E2E; fixtures; AI evals | End-to-end tests, fake payloads, LLM safety test cases.
.github/workflows/ | CI/CD | ci.yml; deploy.yml | Build, lint, test, migration checks, deploy jobs.

## 04A_Repo_Tree
Path | Purpose | Notes
dealflow-ai/
CLAUDE.md | Claude Code instructions | Project rules, stack, guardrails, Definition of Done.
README.md | Developer start guide | Setup, env vars, commands, testing, migrations.
docs/ | Docs | Specs, decisions, backlog, API, schema, runbooks.
apps/web/ | Frontend | Next.js dashboard, inbox, approvals, settings.
apps/api/ | Backend | FastAPI routes, services, integrations, auth, RBAC.
apps/worker/ | Workers | Async workflows, CRM sync, AI jobs, SLA scans.
packages/shared/ | Shared types | Enums, API contracts, constants.
infra/ | Infrastructure | Docker, migrations, seeds, deployment.
scripts/ | Scripts | DB reset, seed, migration, support utilities.
tests/ | Tests | E2E, fixtures, AI evals.
.github/workflows/ | CI/CD | Lint, typecheck, tests, deploy.

## 05_Backend_Structure
Module | Purpose | Example Files | What Belongs Inside
core/ | Cross-cutting backend concerns | auth0.py; rbac.py; errors.py | Config loading, JWT validation, permission checks, error format, rate limits.
db/ | Database session setup | session.py; base.py | SQLAlchemy engine/session, model imports, transaction helpers.
models/ | ORM models | lead.py; message.py; audit_log.py | Database entities and relationships. No business workflow logic.
schemas/ | API schemas | lead.py; approval.py; dashboard.py | Pydantic request/response models and validation.
api/v1/routes/ | HTTP endpoints | leads.py; hubspot.py; twilio.py | Thin route handlers calling services. No heavy business logic.
services/ | Business logic | sla_service.py; routing_service.py | Workflow decisions, validation, orchestration, audit calls.
repositories/ | Data access | lead_repository.py; contact_repository.py | Tenant-scoped queries and persistence helpers.
integrations/ | External providers | hubspot/; twilio/; calendar/ | Provider clients, adapters, mappers, callback verification.
ai/ | AI workflows | prompts/; schemas/; guardrails/; rag/ | Classification, extraction, summary, next-action, RAG, evals.
utils/ | Reusable helpers | phone.py; encryption.py; idempotency.py | Pure utility functions.

## 06_Frontend_Structure
Folder | Purpose | Example Files | What Belongs Inside
app/ | Next.js routes | leads/page.tsx; settings/sla/page.tsx | Page-level routing and layouts.
components/ui/ | Shared UI primitives | button; table; modal | shadcn/ui components and wrappers.
components/timeline/ | Timeline display | LeadTimeline.tsx | Message/action/task/CRM event rendering.
features/leads/ | Lead-specific UI logic | LeadInbox.tsx; LeadDetail.tsx | Lead tables, filters, detail panels.
features/approvals/ | Approval workflow UI | ApprovalQueue.tsx | Approve, edit, reject, manual takeover screens.
features/dashboard/ | Owner dashboard UI | Metric cards; charts | SLA, source, stale, appointment metrics.
features/settings/ | Admin configuration | HubSpot; Twilio; SLA | Forms for tenant-level configuration.
lib/ | Client utilities | api-client.ts; permissions.ts | API wrapper, auth helper, role/permission checks.
types/ | Frontend domain types | api.ts; domain.ts | Shared or generated API response types.

## 07_Database_Structure
Area | Purpose | Example Tables | What Belongs Inside
Tenant/Auth | SaaS isolation | tenants; users; roles; user_roles | Workspace, user, permissions, Auth0 mapping.
Lead Core | Lead operations | lead_sources; contacts; leads; lead_preferences | Normalized leads and qualification data.
Conversations | Messaging | conversations; messages | SMS/WhatsApp/email/iMessage/RCS messages.
AI | AI auditability | ai_actions; human_approvals | Prompt versions, structured outputs, approval queue.
Operations | Sales workflow | lead_assignments; tasks; appointments | Assignment, follow-up, site visit/call booking.
Integrations | Provider connections | integration_connections; crm_mappings; sync_logs | HubSpot/Twilio/calendar config and sync results.
SLA/Consent | Compliance/workflow state | tenant_sla_settings; lead_sla_results; consent_records; opt_out_records | SLA thresholds, stale status, consent, opt-outs.
Audit/Timeline | Trust layer | audit_logs; activity_timeline | Every important action and lead timeline.
Knowledge Base | RAG content | knowledge_documents; knowledge_chunks | PDF/DOCX/TXT/CSV uploads, chunks, embeddings.

## 08_API_Routes
Routes | Route Group | What Belongs Inside
/v1/auth; /v1/me; /v1/tenants; /v1/users | Auth/User | Current user, roles, user management, Auth0 mapping.
/v1/settings/sla; /v1/settings/messaging-channels; /v1/settings/routing | Settings | Tenant SLA, messaging policy, routing, source settings.
/v1/lead-sources; /v1/webhooks/leads/{source_key}; /v1/imports/leads/csv | Lead Sources/Webhooks | Website webhook, email parser endpoint, source validation.
/v1/leads; /v1/leads/{lead_id}; /v1/leads/{lead_id}/timeline; /v1/leads/{lead_id}/assign | Leads | Inbox, detail, update, assignment, timeline.
/v1/leads/{lead_id}/messages; /v1/conversations; /v1/messages | Messages | Send manual/approved messages, receive inbound callbacks.
/v1/human-approvals; /v1/human-approvals/{approval_id}/decision | Approvals | Queue, approve/edit/reject, manual takeover.
/v1/tasks; /v1/appointments/slots; /v1/appointments | Tasks/Appointments | Follow-up tasks, slots, bookings.
/v1/integrations; /v1/integrations/hubspot/connect; /v1/integrations/twilio/connect | Integrations | Provider config, mappings, sync status.
/v1/webhooks/twilio; /v1/webhooks/hubspot | Provider Webhooks | Twilio delivery/inbound callbacks and HubSpot callbacks.
/v1/dashboard/summary; /v1/dashboard/source-performance | Dashboard | Owner dashboard, source performance, SLA metrics.
/v1/audit-logs | Audit | Searchable audit logs.
/v1/kb/documents | Knowledge Base | Document upload, processing status, activation.

## 09_Workers_Integrations_AI
Module | Purpose | Example Files | What Belongs Inside
tasks/ | Atomic async jobs | ai_tasks.py; crm_sync_tasks.py | Queue jobs with retries and idempotency.
workflows/ | Multi-step business flows | new_lead_workflow.py; inbound_message_workflow.py | Orchestrates normalization, AI, messaging, CRM sync.
schedules/ | Recurring jobs | stale_lead_scan.py; crm_retry_scan.py | SLA checks, stale detection, failed sync retry.
dead_letters/ | Failed job handling | handlers.py | Store/report jobs that exceed retry limits.
hubspot/ | First CRM integration | client.py; adapter.py; mapper.py; webhooks.py | OAuth, contact/deal upsert, notes, tasks, mappings, webhooks.
twilio/ | SMS/WhatsApp messaging | client.py; adapter.py; signature.py | Outbound send, inbound callbacks, delivery status, signature validation.
email/ | Email channel | adapter.py; inbound_parser.py; templates.py | Outbound email adapter, inbound parser, templates.
calendar/ | Appointment booking | base.py; google.py; microsoft.py | Google/Microsoft availability, event creation, cancellation.
ai/provider.py | LLM abstraction | provider.py; models.py | Call provider, return structured outputs, handle retries/timeouts.
ai/prompts/ | Versioned prompt templates | lead_classification_v1.md; safety_review_v1.md | Classification, extraction, summary, message draft, safety prompts.
ai/guardrails/ | Safety rules | policy.py; restricted_claims.py; approval_rules.py | Restricted topics, approval triggers, prompt injection checks.
ai/rag/ | Approved knowledge retrieval | document_parser.py; chunker.py; retriever.py | Parse PDF/DOCX/TXT/CSV, chunk, embed, retrieve, cite.

## 10_Testing_Deployment_Docs
Area | Purpose | Example Location | What to Test / What Belongs Inside
Unit tests | Validate isolated logic | apps/api/tests/unit; apps/worker/tests/tasks | RBAC, dedupe, normalization, SLA, consent, guardrails.
Integration tests | Validate module interactions | apps/api/tests/integration | Lead ingestion to DB, Twilio callback to message, HubSpot sync mock.
API tests | Validate endpoints | apps/api/tests/api | Auth, tenant isolation, validation, idempotency.
Worker tests | Validate async jobs | apps/worker/tests/workflows | AI retries, stale scan, CRM retry, notification dispatch.
E2E tests | Validate product flows | tests/e2e | New lead to inbox, approval to message, CRM writeback.
AI evals | Validate AI quality/safety | tests/evals | Classification, extraction, unsafe scenarios, prompt injection.
Deployment | Staging/production infrastructure | infra/deployment | Docker Compose, Render/Railway/Fly configs, deploy scripts.
Documentation | Product and implementation knowledge | docs/ | API contract, schema, integrations, runbooks, pilot checklist.